## October
S. No. | Application | Module | Sub Module | Resource | Job Code | Task Detail |  | Timing detail |  |  | Status | Remarks
[6 empty] | Type | Description | Start date | Expected Completion Date | Actual completed Date
81 | Retiring Room | RR-terminal | room cencellation | Sadhvee/Deba | 42.3 | Bug | Testing appliction special cancellation code Internet mode and teminal mode | 2022-10-03 | 2022-10-03 |  | In Progress
82 | Retiring Room | RR-terminal | room cencellation | Sadhvee/Deba | 42.3 | Bug | Testing appliction special cancellation code Internet mode and teminal mode | 2022-10-03 | 2022-10-06 |  | In Progress
83 | Retiring Room | RR-terminal | room cencellation | Sadhvee/Deba | 42.3 | Bug | Testing appliction special cancellation code Internet mode and teminal mode | 2022-10-06 | 2022-10-06 |  | Completed
84 | Retiring Room | RR-terminal | room book | Deba | 47 | Query | Added room in maintence of MMCT Loction | 2022-10-07 | 2022-10-07 | 2022-10-07 | Completed
85 | Retiring Room | RR-terminal | room book | Sadhvee | 48 | Query | Customers are unable to book retiring room at CPA Stn | 2022-10-07 | 2022-10-10 |  | in progress
86 | Rail Madad |  |  | Sadhvee | 49 |  | rail madad application install | 2022-10-07 | 2022-10-07 | 2022-10-07 | Completed
87 | Retiring Room | RR-terminal | Query | deba | 50 | Query | Customers are unable to book retiring room at CPA Stn | 2022-10-10 | 2022-10-10 |  | Completed
88 | Retiring Room | RR-terminal | Query | deba | 51 | Query | unable to book the retiring room for PNBE station, | 2022-10-10 | 2022-10-14 |  | inprogress | need to solve bug
89 | Rail Madad |  |  | Sadhvee | 52 | login issues | login issues bycrpt problem slove | 2022-10-10 | 2022-10-10 | 2022-10-10 | Completed
90 | Rail Madad |  | KT | Sadhvee | 53 | KT | KT rail madad appliction by Amit jha sir | 2022-10-10 | 2022-10-10 | 2022-10-10 | Completed
91 | Retiring Room | RR-Internet | Bug | deba | 51 | Query | unable to book the retiring room for PNBE station, | 2022-10-10 | 2022-10-14 |  | inprogress | need to solve bug
92 | Retiring Room | RR-Internet | Bug | deba | 51 | Bug | unable to book the retiring room for PNBE station, | 2022-10-10 | 2022-10-14 | 2022-10-12 | Resolved
93 | Retiring Room | RR-Terminal | Deployment | deba/Sadhvee | 55 | Bug | Deployed, Room Extension, RDS and Special cancellation solution on prod | 2022-10-12 | 2022-10-12 | 2022-10-12 | Resolved
94 | Retiring Room | RR-Internet | Maintenance | Deba | 56 | Query | Provided maintenance period (started from to end ) for Aurangabad | 2022-10-13 | 2022-10-13 | 2022-10-13 | Resolved
95 | Retiring Room | RR-Internet | Location Master | Deba | 57 | Change request | Changed 7 rooms of Prayagraj from Deluxe to ordinary | 2022-10-13 | 2022-10-13 | 2022-10-13 | Completed
96 | Retiring Room | RR-Internet | Maintenance | Deba | 58 | Query | Provided maintenance period (started from to end ) for Jalandhar City | 2022-10-13 | 2022-10-13 | 2022-10-13 | Resolved
97 | Retiring Room | RR-Internet | Book Room | Deba | 59 | Query | IRCTC asked to confirm for 141 number of stations retiring room booking activity | 2022-10-13 | 2022-10-13 | 2022-10-13 | Completed
98 | Retiring Room | RR-Internet | Reconciliation File | Deba | 60 | Query | Provided Reconciliation file for 13th October to IRCTC | 2022-10-14 | 2022-10-14 | 2022-10-14 | Completed
97 | Retiring Room | RR-Internet | Book Room | Deba | 61 | Query | Provided IRCTC differential room booking terminal Vs Online | 2022-10-14 | 2022-10-14 | 2022-10-14 | Completed
93 | Retiring Room | RR-Terminal | Room Cancellation | Deba | 62 | Bug | Amritsar Junction reported on room on maintenance mod, Full refund not provided in cancellation | 2022-10-17 | 2022-10-17 | 2022-10-17 | Resolved
94 | Retiring Room | RR-Terminal | Book Room | Deba | 62.1 | QA | Tested Cancellation functionality post bug fix reported by Amritsar | 2022-10-18 | 2022-10-18 | 2022-10-18 | Completed
95 | Retiring Room | RR-Terminal | Migration | Deba | 63 | Migration | Helped Tuhin migrating RR Dev server to new host | 2022-10-18 | 2022-10-18 | 2022-10-18 | Completed
96 | Retiring Room | RR-Terminal | Book Room | Deba | 64 | QA | Dheradun statin raised question on Family Room booking | 2022-10-18 | 2022-10-18 | 2022-10-18 | Completed
97 | RailMadad | Vendor Management | Registration page | Sadhvee | 65 | New Development | create registration page and populate data | 2022-10-18 | 2022-10-18 | 2022-10-18 | Completed
98 | RailMadad | Vendor Management | Registration page | Sadhvee | 65.1 | New Development | create registration page and populate data | 2022-10-18 | 2022-10-18 | 2022-10-18 | Completed
99 | RailMadad | Vendor Management | Registration page | Sadhvee | 65.2 | New Development | multi select dropdown list functionality in registration page and fetch data with api | 2022-10-19 | 2022-10-19 | 2022-10-19 | Completed
100 | Retiring Room | RR-Cloak Room | User Edit | Deba | 64 | QA | Enabled user in RFJ location | 2022-10-19 | 2022-10-19 | 2022-10-19 | Completed
101 | Retiring Room | RR-Terminal | Ticket Cancellation | Deba | 62.2 | Bug | Deployed changed code in production | 2022-10-19 | 2022-10-19 | 2022-10-19 | Completed
102 | Retiring Room | RR-Terminal | Book Room | Deba | 66 | Query | Multiple room booking on same PNR on terminal | 2022-10-19 | 2022-10-19 | 2022-10-19 | Completed
103 | Retiring Room | RR-Terminal | Book Room | Deba | 67 | Query | Raibarelly station raised concern over ticket booking which was failed at the time of booking | 2022-10-19 | 2022-10-19 | 2022-10-19 | Completed
104 | Retiring Room | RR-Terminal | Room maintenance | Deba | 68 | Bug | Mumbai station raused issue, room was on mainteance but still its available for booking | 2022-10-19 | 2022-10-19 | 2022-10-19 | Completed | Couldn’t simulate issue on development. On production mainteance dte passed and now its working fine
105 | Retiring Room | RR-Terminal | Room maintenance Hourly | Deba | 68.1 | Bug | Mumbai station raused issue, room was on mainteance but still its available for booking | 2022-10-20 | 2022-10-20 | 2022-10-20 | Completed | Couldn’t simulate issue on development. On production mainteance dte passed and now its working fine
106 | Retiring Room | RR-Terminal | Book Room | Deba | 69 | Query | Patna Junction asked doubts on GST calculations | 2022-10-20 | 2022-10-20 | 2022-10-20 | Completed
107 | Retiring Room | RR-Terminal | Book Room | Deba | 70 | Query | Kanpur station was facing issue on Room Book. Cleared their Doubt | 2022-10-20 | 2022-10-20 | 2022-10-20 | Completed
108 | RailMadad | Vendor Management | Registration page | Sadhvee | 65.3 | New Development | create responsive registration page and manage code | 2022-10-20 | 2022-10-20 | 2022-10-20 | Completed
109 | RailMadad | Vendor Management | Registration page | Sadhvee | 65.4 | New Development | token session in registration page with ajax an jquery | 2022-10-21 | 2022-10-22
110 | RailMadad | Vendor Management | Registration page | Sadhvee | 65.4 | New Development | token session in registration page with ajax an jquery | 2022-10-21 | 2022-10-22 | 2022-10-22 | Completed
111 | Retiring Room | RR-Terminal | Room maintenance | Deba | 71 | Maintenance | Blocked booking on SLN station untill 2099. | 2022-10-21 | 2022-10-21 | 2022-10-21 | Completed
112 | Retiring Room | RR-Internet | Room maintenance | Deba | 72 | Query | Updated IRCTC about KGP, NJP stations maintenance date. Reoprted issue found to be on IRCTC end | 2022-10-21 | 2022-10-21 | 2022-10-21 | Completed
113 | Retiring Room | RR-Internet | Reconciliation File | Deba | 73 | Query | Provided Reconciliation file for 22nd,23rd October to IRCTC | 2022-10-25 | 2022-10-25 | 2022-10-25 | Completed
114 | Retiring Room | RR-Terminal | Book Room | Deba | 74 | Bug | RFJ Station raised concern on Room availability for their location. Tried to simulate same in enviorment but no issue noticed | 2022-10-25 | 2022-10-25 | 2022-10-25 | Completed
115 | Retiring Room | RR-Terminal | Deployment | Deba | 75 | Bug | Heap Dump error noticed frequebntly on Jboss logs. Trying to find solution | 2022-10-25 | 2022-11-01 |  | InProgress
116 | RailMadad | Vendor Management | Registration page | Sadhvee | 65.5 | New Development | complete vendor registration . | 2022-10-25 | 2022-10-25 | 2022-10-25 | Completed
117 | RailMadad | Vendor Management | Registration page | Sadhvee | 65.6 | New Development | add more option explore , and complete vendoer login | 2022-10-26 | 2022-10-26 | 2022-10-26 | Completed
118 | Retiring Room | RR-Terminal | Migration | Deba | 63.1 | Migration | Configured RR Development enviornment in new serverst | 2022-10-26 | 2022-10-26 | 2022-10-26 | Completed
119 | Retiring Room | RR-Internet | Book Room | Deba | 76 | Bug | Slot time was showing wrongly on SIKR station. Found to be wrong data entry. Fixed the issue updating database | 2022-10-26 | 2022-10-26 | 2022-10-26 | Completed
120 | RailMadad | Vendor Management | Registration page | Sadhvee | 65.7 | New Development | impletement validation on registration page | 2022-10-27 | 2022-10-27 |  | in progress
121 | Retiring Room | RR-Internet | Maintenance | Deba | 76 | Query | Provided maintenance period (started from to end ) for Bhubaneswar | 2022-10-27 | 2022-10-27 | 2022-10-27 | Resolved
122 | Retiring Room | RR-Terminal | BookRoom/Extension | Deba | 77 | Change request | Enabled facility for 3 passengers to book 2 double room | 2022-10-27 | 2022-10-30 |  | InProgress
123 | Retiring Room | RR-Terminal | Deployment | Deba | 78 | Bug | RR Code cleanup | 2022-10-27 | 2022-10-30 |  | InProgress
124 | Retiring Room | RR-Internet | BookRoom/Extension | Deba | 79 | Change request | Enabled facility for 3 passengers to book 2 double room | 2022-10-28 | 2022-11-01 |  | InProgress
125 | Retiring Room | RR-CloakRoom | Deployment | Deba | 80 | New Development | Deployed RR CloakRoom and fixed connection issue | 2022-10-28 | 2022-10-28 | 2022-10-28 | Resolved
126 | Retiring Room | RR-Internet | PNR Enquiry | Deba | 81 | Query | IRCTC raised query over PNR check | 2022-10-28 | 2022-10-28 | 2022-10-28 | Resolved
127 | Retiring Room | RR-CloakRoom | Login | Deba | 82 | Query | two users in MZP were unable to login, found they skipped forced logout | 2022-10-31 | 2022-10-31 | 2022-10-31 | Resolved
128 | Retiring Room | RR-Terminal | PNR Enquiry | Deba | 83 | Query | Bhubaneswar complained they are unable to book room, found rooms are on different quotas and booked | 2022-10-31 | 2022-10-31 | 2022-10-31 | Resolved
129 | Retiring Room | RR-Terminal | Ticket Printing | Deba | 84 | Query | Sewagram railway station raised query over ticket printing issue | 2022-11-01 | 2022-11-01 | 2022-11-01 | Resolved
130 | Retiring Room | RR-Terminal | Reports | Deba | 85 | Reports | Retiring Room Monthly report preparation | 2022-11-01 | 2022-11-01 | 2022-11-01 | Resolved

## Sheet1
104 | RailMadad | Vendor Management | Registration page | Sadhvee | 65.7 | New Development | impletement validation on registration page | 2022-10-27 | 2022-10-27 | in progress

## September
S. No. | Application | Module | Sub Module | Resource | Job Code | Task Detail |  | Timing detail |  |  | Status | Remarks
[6 empty] | Type | Description | Start date | Expected Completion Date | Actual completed Date
26 | Retiring Room | RR-terminal | Room Cancel | Deba | 11 | Query | Sealdah station raised query over ticket cancellation | 2022-09-01 | 2022-09-01 | 2022-09-02 | Resolved
27 | Retiring Room | RR-Internet | Soap Service | Sadhvee | 10.5 | New Development | Completed CSV file for balance enquiry service | 2022-09-01 | 2022-09-01 | 2022-09-02 | Completed
28 | Retiring Room | RR-terminal | Extension | Deba | 4.2 | Bug | GST calculation not showing properly for Room Extension | 2022-08-22 | 2022-08-24 | 2022-09-02 | Completed
29 | Retiring Room | RR-Internet | Soap Service | Sadhvee | 10.6 | New Development | Completed CSV file for balance enquiry service with validation | 2022-09-02 | 2022-09-02 | 2022-09-02 | Completed
30 | Retiring Room | RR-Internet | Maintenance | Deba | 12 | Query | Provided maintenance period (started from to end ) for BARMER | 2022-09-05 | 2022-09-05 | 2022-09-02 | Completed
31 | Retiring Room | RR-Internet | Reconciliation File | Deba | 13 | Query | Provided Reconciliation file for 4th September to IRCTC | 2022-09-05 | 2022-09-05 | 2022-09-05 | Completed
32 | Retiring Room | RR-Internet | Room Cancellation | Deba | 14 | Bug | While Cancelling booking showing error | 2022-09-05 | 2022-09-05 | 2022-09-05 | Completed | Multiple cancellation request sent, On 1st request ticket was cancelled. Next requests failed. It s not a bug at our end
33 | Retiring Room | RR-terminal |  | Deba |  | KT | KT to help desk | 2022-09-06 | 2022-09-06 | 2022-09-06 | Completed | KT on Room Edit
34 | Retiring Room | RR-terminal | Reports | Deba | 17 | Enhancement | New reports and enhancement of old reports | 2022-09-06 | 2022-09-09 |  | In Progress | Need jasper 3.7.2 version to develop new reports
35 | Retiring Room | RR-Internet | Room Cancellation | Deba | 16 | Bug | While Cancelling booking No response from server | 2022-09-06 | 2022-09-06 | 2022-09-06 | Completed | Multiple cancellation request sent, On 1st request ticket was cancelled. Next requests failed. It s not a bug at our end
36 | Retiring Room | RR-Internet | Maintenance | Deba | 18 | Query | Provided maintenance period (started from to end ) for KIR & KPD | 2022-09-07 | 2022-09-07 | 2022-09-07 | Completed
37 | Retiring Room | RR-terminal |  | Deba |  | KT | KT to help desk on Room Edit by supervisor user as this feature enabled today | 2022-09-07 | 2022-09-07 | 2022-09-07 | Completed | KT on Room Edit
38 | Retiring Room | RR-terminal | Room Edit | Deba | 7.1 | Deployment | Deployed room edit feature for Supervisor user in RR Production both servers | 2022-09-07 | 2022-09-07 | 2022-09-07 | Completed
39 | Retiring Room | RR-terminal | Reports | Deba | 17.1 | Enhancement | New reports and enhancement of old reports | 2022-09-06 | 14/9/2022 |  | In Progress
40 | Retiring Room | RR-terminal | PNR Activity | Deba |  | KT | KT to Pradeep and helpdesk on PNR activity | 2022-09-08 | 2022-09-08 | 2022-09-08 | Completed
41 | Retiring Room | RR-Internet | Maintenance | Deba | 19 | Query | Provided maintenance period (started from to end ) for HJP | 2022-09-09 | 2022-09-09 | 2022-09-09 | Completed
42 | Retiring Room | RR-terminal | RDS | Deba | 20 | KT | Displaying currency in words | 2022-09-09 | 2022-09-12 |  | In Progress
43 | Retiring Room | RR-terminal | Room Book | Deba | 21 | Query | Erode JN station raised query over ticekt booing, which was failed due to server restart | 2022-09-10 | 2022-09-10 | 2022-09-10 | Resolved
44 | Retiring Room | Cloak Room | User Edit | Deba | 22 | Query | Enabled user bdlnunnab for BDL station | 2022-09-12 | 2022-09-12 | 2022-09-12 | Completed
45 | Retiring Room | RR-terminal | RDS | Deba/sadhvee | 20.1 | Enhancement | Displaying currency in words | 2022-09-12 | 2022-09-13 |  | In Progress
46 | Rail madad | Database | deployment | Sadhvee | 23 | Deployment | Issue find out and solve | 2022-09-12 | 2022-09-12 | 2022-09-12 | Completed
47 | Retiring Room | Cloak Room | room book | Deba | 24 | Query | GHY station raised concern over room booking for 26th Sepetember | 2022-09-12 | 2022-09-12 | 2022-09-12 | Completed
48 | Retiring Room | RR-terminal | RDS | Sadhvee | 20.2 | Enhancement | Displaying currency in words | 2022-09-12 | 2022-09-14 |  | In Progress
49 | Retiring Room | RR-Internet | Maintenance | Deba | 25 | Query | IRCTC had query on tickey cancellation, of a user when cris network had issue | 2022-09-13 | 2022-09-13 | 2022-09-13 | Resolved
50 | Retiring Room | RR-Internet | Maintenance | Deba | 26 | Query | Provided maintenance period (started from to end ) forSurat | 2022-09-14 | 2022-09-14 | 2022-09-14 | Resolved
51 | Retiring Room | RR-terminal | Reports | Deba | 27 | Report | Provided terminals detail report for NFR Zone | 2022-09-14 | 2022-09-14 | 2022-09-14 | Completed
52 | Retiring Room | RR-terminal | RDS | sadhvee | 20.3 | Enhancement | Displaying currency in words | 2022-09-12 | 2022-09-14 | 2022-09-14 | Completed
53 | Retiring Room | RR-terminal | Room Book | Deba | 28 | Query | Roombook was initiated by IRCTC but was incomplete, While checkin in terminal railway user faced issue with that, We identified root cause and informed IRCTC for correction | 2022-09-14 | 2022-09-14 | 2022-09-14 | Resolved
54 | Retiring Room | RR-terminal | RDS | sadhvee | 30 | Enhancement | Displaying currency in words agent_deposit_confirm.xhtml and deposit_amount_succes.xhml | 2022-09-15 | 2022-09-15 | 2022-09-15 | Completed
55 | Retiring Room | RR-Internet | Room Book | Deba | 31 | Bug | Room booking nort working for short distance travel where station on hourly mode | 2022-09-15 | 2022-09-16 |  | In Progress | Have dependency on IRCTC as their UAT site not working
56 | Retiring Room | RR-terminal | Room Book | Deba | 32 | Bug | Ticket booking was failing bnetween station Jodhpur and Sabarmati BG | 2022-09-16 | 2022-09-16 | 2022-09-16 | Completed | Have dependency on IRCTC as their UAT site not working
57 | Retiring Room | RR-terminal | RDS | sadhvee | 30.1 | Enhancement | Displaying currency in words agent_deposit_confirm.xhtml and deposit_amount_succes.xhml | 2022-09-15 | 2022-09-16 | 2022-09-16 | Completed
58 | Retiring Room | RR-terminal | Terminal | sadhvee | 31 | Bug | fixed bug in Originating Earnings summary report for intenet option | 2022-09-19 | 2022-09-19 | 2022-09-19 | Completed
59 | Retiring Room | RR-terminal | Room Book | Deba | 32 | Query | Room inventory details of KLK station. | 2022-09-19 | 2022-09-19 | 2022-09-19 | Completed
60 | Retiring RoomRR-terminal |  | Room Book | Deba | 31.1 | Bug | Room booking nort working for short distance travel where station on hourly mode | 2022-09-20 | 2022-09-23 |  | In Progress
61 | Retiring Room | Cloak Room | room book | Deba | 33 | Query | Added room in maintence of MMCT Loction | 2022-09-21 | 2022-09-21 | 2022-09-21 | Completed
62 | Retiring Room | New Development | login functionality | Sadhvee | 34 | New Development | New development for learning purpose in spring boot | 2022-09-22 | 2022-09-22 | 2022-09-22 | Completed
62 | Retiring Room | New Development | login functionality | Sridhar | 35 | New Development | New development for learning purpose in flutter | 2022-09-23 | 2022-09-23 | 2022-09-23 | Completed
61 | Retiring Room | RR-Internet | room book | Deba | 36 | Query | Testing appliction for Added room in maintence of MMCT Loction | 2022-09-22 | 2022-09-23 | 2022-09-23 | Completed
62 | Retiring Room | New Development | login functionality | Sadhvee | 34.1 | New Development | New development for learning purpose in spring boot | 2022-09-22 | 2022-09-23 | 2022-09-23 | Completed
63 | Retiring Room | New Development | login functionality | Sridhar | 35.1 | New Development | New development for learning purpose in flutter | 2022-09-22 | 2022-09-23 | 2022-09-23 | Completed
64 | Retiring Room | RR-Internet | Recon File | Deba | 37 | Query | generate and send recon Reconciliation file dated 22-09-22 to irctc | 2022-09-23 | 2022-09-23 | 2022-09-23 | Completed
65 | Retiring Room | New Development | login functionality | Sadhvee | 34.2 | New Development | create login API with session | 2022-09-23 | 2022-09-26 |  | In progess
66 | Retiring Room | New Development | login functionality | Sridhar | 35.2 | New Development | New development for learning purpose in flutter with database Connectivity | 2022-09-23 | 2022-09-26 | 2022-09-26 | Completed
67 | Retiring Room | New Development | login functionality | Sridhar | 38 | Query | Enabled user rfjmjk.rfjpip, rfjrkd, rfjrkr, for RFJ station | 2022-09-23 | 2022-09-23 |  | Completed
68 | Retiring Room | RR-terminal |  | Deba | 39 | KT | KT to Pradeep and helpdesk on RR Application | 2022-09-23 | 2022-09-23 |  | Completed
69 | Retiring Room | New Development | login functionality | Sadhvee | 40 | New Development | Learning SpringBoot Annotation and JWT Token | 2022-09-23 | 2022-09-26 |  | Completed
70 | Retiring Room | New Development | login functionality | Sridhar | 41 | New Development | New development for learning purpose in flutter with API Connectivity | 2022-09-23 | 2022-09-26 |  | Completed
71 | Retiring Room | RR-terminal | room book | Deba | 42 | Query | System is not giving special cancellation | 2022-09-27 | 2022-09-27 |  | Completed | need to solve bug
72 | Retiring Room | New Development | login functionality | Sadhvee | 43 | New Development | Learning SpringBoot JPA and Jjdbc | 2022-09-27 | 2022-09-27 |  | Completed
73 | Retiring Room | New Development | login functionality | Sridhar | 41.1 | New Development | New development for learning purpose in flutter with API Connectivity | 2022-09-27 | 2022-09-28 |  | Completed
74 | Retiring Room | RR-terminal | room book | Deba | 42.1 | Query | System is not giving special cancellation code review | 2022-09-28 | 2022-09-28 |  | Completed | need to solve bug
75 | Retiring Room | New Development | login functionality | Sadhvee | 43.1 | New Development | Learning SpringBoot JPA and Jjdbc | 2022-09-28 | 2022-09-28 |  | Completed
76 | Retiring Room | RR-terminal | User Edit | Sridhar | 44 | Query | Enbled user at ambala station | 2022-09-28 | 2022-09-28 |  | Completed
77 | Retiring Room | RR-terminal | room cencellation | Deba /Sadhvee | 42.1 | Bug | System is not giving special cancellation code | 2022-09-29 | 2022-10-03 |  | In Progress
78 | Retiring Room | RR-terminal | Query | Sridhar | 45 | Query | change room status type AC to NON-AC at KURJ station | 2022-09-29 | 2022-09-29 |  | Completed
79 | Retiring Room | RR-terminal | room cencellation | Deba /Sadhvee | 42.1 | Bug | Bug fixed System is not giving special cancellation code | 2022-09-30 | 2022-10-03 |  | In Progress | Have dependency on IRCTC because UAT RR Tickets for testing purpose
80 | Retiring Room | RR-terminal | Query | Sadhvee | 46 | Query | Provided DTC report to Station DDN | 2022-09-30 | 2022-09-30 |  | Completed
81 | Retiring Room | RR-terminal | room cencellation | Sadhvee/Deba | 42.3 | Bug | Testing appliction special cancellation code Internet mode and teminal mode | 2022-10-03 | 2022-10-03 |  | In Progress
82 | Retiring Room | RR-terminal | room cencellation | Sadhvee/Deba | 42.3 | Bug | Testing appliction special cancellation code Internet mode and teminal mode | 2022-10-03 | 2022-10-06 |  | In Progress
83 | Retiring Room | RR-terminal | room cencellation | Sadhvee/Deba | 42.3 | Bug | Testing appliction special cancellation code Internet mode and teminal mode | 2022-10-06 | 2022-10-06 |  | Completed
84 | Retiring Room | RR-terminal | room book | Deba | 47 | Query | Added room in maintence of MMCT Loction | 2022-10-07 | 2022-10-07 | 2022-10-07 | Completed
85 | Retiring Room | RR-terminal | room book | Sadhvee | 48 | Query | Customers are unable to book retiring room at CPA Stn | 2022-10-07 | 2022-10-10 |  | in progress
86 | Rail Madad |  |  | Sadhvee | 49 |  | rail madad application install | 2022-10-07 | 2022-10-07 | 2022-10-07 | Completed
87 | Retiring Room | RR-terminal | Query | deba | 50 | Query | Customers are unable to book retiring room at CPA Stn | 2022-10-10 | 2022-10-10 |  | Completed
88 | Retiring Room | RR-terminal | Query | deba | 51 | Query | unable to book the retiring room for PNBE station, | 2022-10-10 | 2022-10-14 |  | inprogress | need to solve bug
89 | Rail Madad |  |  | Sadhvee | 52 | login issues | login issues bycrpt problem slove | 2022-10-10 | 2022-10-10 | 2022-10-10 | Completed
90 | Rail Madad |  | KT | Sadhvee | 53 | KT | KT rail madad appliction by Amit jha sir | 2022-10-10 | 2022-10-10 | 2022-10-10 | Completed
91 | Retiring Room | RR-Internet | Bug | deba | 51 | Query | unable to book the retiring room for PNBE station, | 2022-10-10 | 2022-10-14 |  | inprogress | need to solve bug
92 | Retiring Room | RR-Internet | Bug | deba | 51 | Bug | unable to book the retiring room for PNBE station, | 2022-10-10 | 2022-10-14 | 2022-10-12 | Resolved
93 | Retiring Room | RR-Terminal | Deployment | deba/Sadhvee | 55 | Bug | Deployed, Room Extension, RDS and Special cancellation solution on prod | 2022-10-12 | 2022-10-12 | 2022-10-12 | Resolved

## August
S. No. | Application | Module | Sub Module | Resource | Job Code | Task Detail |  | Timing detail |  |  | Status | Remarks
[6 empty] | Type | Description | Start date | Expected Completion Date | Actual completed Date
1 | Retiring Room | RR-Internet | Cancellation | Deba | 1 | Bug | Refudn should be given 50% slab while it is happening in 0% slab where cancellation is being performed after 23:00 hrs | 2022-08-16 | 2022-08-18 | 2022-08-18 | Closed | Fixed and deployed in development for testing
2 | Retiring Room | RR-terminal | Rating | Sadhvee | 9 | New Development | Showing of the rating for last 30 days | 2022-08-10 |  |  | Under development
3 | Retiring Room | RR-terminal | Cancellation Issue | Deba | 2 | Bug | On RR-Terminal in certain condition unable to cancel ticket. | 2022-08-18 | 2022-08-18 | 2022-08-18 | Closed | Couldn’t Simulate bug in local environment
4 | Retiring Room | RR-terminal | Rating | Sadhvee | 9.1 | New Development | Showing of the rating for last 30 days | 2022-08-10 | 2022-08-18 | 2022-08-18 | Closed | Bar chart pending
5 | Retiring Room | RR-terminal | Rating | Sadhvee | 9.2 | New Development | Implement Bar Chart for Rating Summary | 2022-08-22 | 2022-08-22 |  | Closed | Bar chart pending
6 | Retiring Room | RR-terminal | Extension | Deba | 3 | Bug | Hourly GST calculation not showing properly for Room Extension | 2022-08-22 | 2022-08-24 | 2022-08-24 | Completed
7 | Retiring Room | RR-terminal | Book Room | Deba | 4 | Query | DBA station raised query about their last activity for RR | 2022-08-22 | 2022-08-22 | 2022-08-22 | Closed
8 | Retiring Room | RR-terminal | Rating | Sadhvee | 9.3 | New Development | Implement Bar Chart for Rating Summary | 2022-08-22 | 2022-08-22 |  | In Progress
9 | Retiring Room | RR-Internet | Booking | Deba | 5 | Bug | Unable to book room for PCOI station | 2022-08-22 | 23/08/2022 | 23/08/2022 | Issue Fixed | Deployed in Production
10 | Retiring Room | RR-terminal | Extension | Deba | 4.1 | Bug | GST calculation not showing properly for Room Extension | 2022-08-22 | 2022-08-24 |  | Completed
11 | Retiring Room | RR-terminal | Rating | Sadhvee | 9.4 | New Development | Rating finished and completed deployment work | 2022-08-24 | 2022-08-24 | 2022-08-24 | Completed
12 | Retiring Room | RR-Internet | Cancellation Issue | Deba | 1.1 | Bug | Deployed in production, resolved issue 11pm-12am cancellation issue | 2022-08-24 | 2022-08-24 | 2022-08-24 | Completed
13 | Retiring Room | RR-terminal | Room Add | Deba | 6 | Enhancement | Provided feature to toggle between Ac/Non Ac. Deployed in development | 2022-08-24 | 2022-08-24 | 2022-08-24 | Completed
14 | Retiring Room | RR-terminal | Room Add | Deba | 6.1 | Enhancement | Provided feature to toggle between Room Type Floor Type. Deployed in development | 2022-08-25 | 2022-08-25 | 2022-08-25 | Completed
15 | Retiring Room | RR-Internet | Soap Service | Sadhvee | 10 | New Development | Web service implement for Balance Inquiry | 2022-08-25 | 2022-08-25 |  | In Progress
16 | Retiring Room | RR-terminal | Room Edit | Deba | 7 | Enhancement | Enable edit log for room edit and allow, supervisors to edit rooms | 2022-08-26 | 2022-08-30 |  | Completed
17 | Retiring Room | RR-Internet | Room Book | Deba | 8 | Bug | IRCTC Reported same room booked twice for same slot | 2022-08-26 | 2022-08-26 | 2022-08-26 | Closed | Couldn’t be simulated so closed
18 | Retiring Room | RR-Internet | Soap Service | Sadhvee | 10.1 | New Development | Web service implement for Balance Inquiry | 2022-08-25 | 2022-08-27 |  | In Progress
19 | Retiring Room | RR-terminal | Room checkout | Deba | 11 | Bug | BSBS station reported they are unable to checkout a booking | 2022-08-29 | 2022-08-29 | 2022-08-29 | Completed | Fixed the bug and deployed in development
20 | Retiring Room | RR-Internet | Soap Service | Sadhvee | 10.2 | New Development | Web service implement for Balance Inquiry | 2022-08-25 | 2022-08-27 | 2022-08-27 | In Progress | Assigned target 3 days
21 | Retiring Room | RR-terminal | Extension | Deba/Sadhvee | 3.1 | Bug | GST calculation not showing properly for Room Extension | 2022-08-22 | 2022-08-24 |  | Completed | Issue resolved, Deployed in Dev server for testing
22 | Retiring Room | RR-Internet | Soap Service | Sadhvee | 10.3 | New Development | Implement validation in balance enquiry service | 2022-08-30 | 2022-08-30 | 2022-08-30 | Completed
23 | Retiring Room | RR-Internet | Soap Service | Sadhvee | 10.4 | New Development | Implement CSV file for balance enquiry service | 2022-08-31 | 2022-09-01 |  | In Progress
24 | Retiring Room | RR-terminal |  | Deba |  | KT | KT to help desk | 2022-08-31 | 2022-08-31 |  | Completed
25 | Retiring Room | RR-terminal | Extension | Deba | 3.2 | Bug | GST calculation not showing properly for Room Extension | 2022-08-22 | 2022-08-24 | 2022-09-02 | Completed | New Bug noticed